## Sheet2
Task Name | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
| 16/09/2023 - 20/09/2023 | 25/09/2023 - 29/09/2023 | 02/10/2023 - 06/10/2023 | 09/10/2023 - 13/10/2023 | 16/10/2023 - 20/10/2023 | 23/10/2023 - 27/10/2023 | 30/10/2023 - 03/11/2023 | 06/11/2023 - 10/11/2023 | 13/11/2023 - 17/11/2023 | 20/11/2023 - 24/11/2023 | 27/11/2023 - 01/12/2023 | 04/11/2023 - 08/12/2023 | 11/11/2023 - 15/12/2023
Data Science Research | bar: WEEK 1 to WEEK 4
Data Collection | bar: WEEK 3 to WEEK 6
Product Planning | bar: WEEK 1 to WEEK 4
Upload File | bar: WEEK 2 to WEEK 3
Display File | bar: WEEK 3 to WEEK 4
Parse File | bar: WEEK 3 to WEEK 5
Font style | bar: WEEK 4
Font size | bar: WEEK 5
Layout-alignment | bar: WEEK 5
Colour - Contrast | bar: WEEK 6
Colour - Dyslexia | bar: WEEK 6 to WEEK 7
Headings | bar: WEEK 6 to WEEK 7
Paragraph | bar: WEEK 7 to WEEK 11
Dyslexia ruler with customisations | bar: WEEK 7 to WEEK 8
Text to speech | bar: WEEK 8 to WEEK 9
Screen Reader | bar: WEEK 9 to WEEK 10
Bad words | bar: WEEK 7 to WEEK 9
Image labelling | bar: WEEK 8 to WEEK 10
Expand Abbreviations and simplify jargon | bar: WEEK 10 to WEEK 13
Glossary Auto-generation | bar: WEEK 10 to WEEK 13
Layout -Table of Contents | bar: WEEK 10 to WEEK 12
Survey | bar: WEEK 6 to WEEK 13
UI Development | bar: WEEK 2 to WEEK 10
Layout – Sentence chunking & Sentence splitting | bar: WEEK 11 to WEEK 13
User Testing | bar: WEEK 8 to WEEK 13